## Communication Plan
Interactions for Student Recruitment Implementation Communication Plan
Targeted Scheduled Dates | Type of Message/Activity | Communication Message Purpose or Key-Points | PowerPoint or Other Presentation | Meeting Request | Face-to-Face Meeting | Online Meeting | Lunch & Learn | Email | Letter | Training Materials | Team Celebration | Chatter | Frequency of Recurring Messages/Activities | Who is the Author? | IT Leadership | Impelmentation Team | Power Users | Users | All Stakeholders | Third Party Vendors | Others | Who is the Responsible for the Delivery of the Message? | Status
|  |  | Communication Vehicle(s) | [11 empty] | Audience(s)
Stage 1 - Pre-Kick-Off Activities and Communication
This may be completed during/after Discovery (see Project Plan) | Project Branding | Identify a logo or tag line that can be used as a branding tool for the project to increase user adoption |  | x |  |  |  | x |  |  |  |  | Once | Project and Marketing Team |  | x | x |  | x |  |  | Marketing Team
Prior to actual project kick-off date | General Announcement | Announce the project and convey that it is strategic in nature and will positively impact the institution. Additionally, provide general information about the project. | [5 empty] | x |  |  |  | x | Once | Project Team | x | x | x | x | x | x |  | Marketing Team
Prior to actual project kick-off date | Develop Communication Templates | Develop communications media and templates: -Project Newsletter -Email -PowerPoint | x |  |  |  |  | x |  | x |  |  | Once | IT Communication Team | [7 empty] | IT Communication Team
Stage 2 - Project Kick-Off Communications and Event
| Project Kick-off -Email Announcement -Meeting Invite -Reminder Invite -Reminder Event Tomorrow | Key Message: - Reason for upgrade - Benefits of upgrade - Impacted Audience/Audience Groups - Anticipated Timeline |  | x |  |  |  | x |  |  |  | x | Begin 3 weeks before event. Week 1: Announcement and Outlook Invite Week 2: Invite Reminder Week 3: Event Tomorrow Reminder Day after Week 3: Event | Salesforce Team | x | x | x |  |  | x |  | Project Team
| Additional Project Kick-off Sessions | Key Message: - Reason for upgrade - Benefits of upgrade - Impacted Audience/Audience Groups - Anticipated Timeline |  |  | x | [7 empty] | As needed | Salesforce Team | [7 empty] | Project Team
| Follow-up Chatter Communications | Provide status update and timeline detailing what has been accomplished to date, work in progress, and what the team expects to accomplish over the next period. Reiterate project benefits and why we are upgrading. Include who to contact with questions and mechanism for contacting. | [9 empty] | x | Weekly | Salesforce Team |  | x | x | x |  |  |  | Project Team
| Gather and respond to feedback, questions from ongoing general communications | As appropriate | [5 empty] | x |  |  |  | x | As needed | Salesforce Team | [7 empty] | Project Team
| Develop Key Talking Points for Leadership | Talking points re: project changes, key messages and benefits which can be used by management during staff meetings, and to respond to questions from stakeholders. | x |  |  |  |  | x |  |  |  |  | Monthly | Salesforce Team | x | [6 empty] | Project Team
Regularly Scheduled Meetings
| Project Management | Status update, accomplishments, cross functional concerns, issues. | [5 empty] | x |  |  |  |  | Monthly | Salesforce Team | [6 empty] | x | Project Team
| User Group Meetings | Project Status Update from Project Managers and Leads, milestones, accomplishments, issues, concerns, |  | x | x | [6 empty] | x | Monthly | Salesforce Team |  | x | x | x |  |  |  | Salesforce Team
| Update Meetings | Project Status Update from Project Managers and Leads, milestones, accomplishments, issues, concerns, |  | x |  | x | [5 empty] | x | Weekly | Salesforce Team |  | x | x |  |  |  |  | Project Team
Project Contact Info
| Core Project Team Contact List | Facilitates communication between project teams and individuals | [9 empty] | x | Once | Salesforce Team |  | x | x | x |  |  |  | Project Team
| Functional Business Owners, Subject Matter Experts (SME) Contact List | Facilitates communication between the core project team, business owners and SME's | [9 empty] | x | Once | Salesforce Team |  | x | x | x |  |  |  | Project Team
FAQs / Glossary
| Create FAQ's to facilitate sharing of knowledge | Create repository of Salesforce information | [7 empty] | x |  | x | Monthly | Salesforce Team |  | x | x | x |  |  |  | Salesforce Team
| Create Glossary to facilitate understanding of terms | Create repository of Salesforce information | [7 empty] | x |  | x | Monthly | Salesforce Team |  | x | x | x |  |  |  | Salesforce Team
Awareness Campaign
| Quarterly Salesforce Newletter | Updates and plans for next quarter | [5 empty] | x |  |  |  | x | Quarterly | Salesforce Team |  | x | x | x |  |  |  | Project Team
| Awareness Campaigns | Demonstrations, presentations and product bulletins that highlight the advantages offered by the change in functionality. |  |  | x | [7 empty] | As needed | Project Team |  |  | x | x | x |  |  | Project Team
| Press Release(s) | [11 empty] | As needed | Marketing Team | [6 empty] | x | Marketing Team
Lunch and Learn Sessions
| Lunch and Learn Sessions | Scheduled sessions (not to be considered as end user training) to provide an opportunity for hands-on experience with the upgraded Salesforce system and to promote buy-in and ownership and to prepare the UAT team for testing. |  |  |  |  | x | [5 empty] | Weekly | Salesforce Team |  |  | x | x | x |  |  | Salesforce Team
Team Milestone Celebrations
| Complete Project Phase | Opportunity to express job well done |  |  | x | [6 empty] | x | As needed | Project Team | x | x | x | x | x | x |  | Project Team
UAT Testing
| Invitation to participate in Data Validation Sessions | Data Validation testing prior to Go-Live. Acceptance of the new system is dependent upon validation of the new business processes and system functionality. |  | x |  |  |  | x |  |  |  | x | Begin 3 weeks before event. Week 1: Announcement and Outlook Invite Week 2: Invite Reminder Week 3: Event Tomorrow Reminder Day after Week 3: Event | Salesforce Team |  | x | x |  |  |  |  | Salesforce Team
End User Training
| Communication to announce upcoming end user training and to put emphasis on the importance of the training | Generate excitement and set expectations for end user training and to put emphasis on the importance of active participation | [5 empty] | x |  |  |  | x | As needed | Salesforce Team |  | x | x | x |  |  |  | Salesforce Team
| Power User Training - Communication to announce the schedule, sign-up procedures for classes, etc. | Schedule and timeline for end user training. | [5 empty] | x |  |  |  | x | Begin 3 weeks before event. Week 1: Announcement and Outlook Invite Week 2: Invite Reminder Week 3: Event Tomorrow Reminder Day after Week 3: Event | Salesforce Team |  |  | x |  |  |  |  | Salesforce Team
| User Training - Communication to announce the schedule, sign-up procedures for classes, etc. | Schedule and timeline for end user training. | [5 empty] | x |  |  |  | x | Begin 3 weeks before event. Week 1: Announcement and Outlook Invite Week 2: Invite Reminder Week 3: Event Tomorrow Reminder Day after Week 3: Event | Salesforce Team |  |  | x |  |  |  |  | Salesforce Team
| Training Evaluation | Evaluation of trainers and training materials | [10 empty] | Following user trainings | Project Team | [7 empty] | Project Team
Pre Go-Live Communications
| Go-Live Announcements | Series of go-live announcements sent to all stakeholder groups. The message will include changing business practices, how you will be impacted, why, who to contact with questions and other information as required. | [5 empty] | x |  |  |  | x |  | Salesforce Team |  |  | x | x |  |  |  | Project Team
Post Go-Live Communications
| Thank you Letters | Letter to thank applicable team members including core team, testers, developers, trainers, etc. for their contributions to the project. | [6 empty] | x |  |  |  | Once | Project Team |  | x | x |  |  |  |  | Project Team
Vendor Communications
| Notification of Non-renewal | Letter delivered to vendor terminating their relationship with the University, for any vendors replaced with Salesforce. | [6 empty] | x |  |  |  | Once