## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Notes | Resource Names | % Complete
Interactions for Student Recruitment Implementation
Phase 1 - Review Documentation | [6 empty] | 0%
Review HEDA trailhead | [6 empty] | 0%
Review Interactions for Student Recruitment User Guide | [6 empty] | 0%
Review Interactions for Student Recruitment Learning Guide | [6 empty] | 0%
Review Interactions for Student Recruitment Implementation and Configuration Guide | [6 empty] | 0%
Review Interactions for Student Recruitment Technical Implementation Guide | [6 empty] | 0%
Phase 2 - Discovery and Model Review | [6 empty] | 0%
Write-up Objectives | [6 empty] | 0%
Compile objectives | [6 empty] | 0%
Attain buy-in from executives and end users | [6 empty] | 0%
Gather Requirements | [6 empty] | 0%
Complete Discovery document | [6 empty] | 0%
Identify items out of scope | [6 empty] | 0%
Update model to reflect in scope items only | [6 empty] | 0%
Review final model and approve for Production build out | [6 empty] | 0%
Phase 3 - Coordinate and Communicate Project Kick Off | [6 empty] | 0%
Finalize Project Timelines, Communication, and Training Plans | [6 empty] | 0%
Coordinate resources for pre-implementation requirements | [6 empty] | 0%
Schedule project update meetings | [6 empty] | 0%
Kick-off project | [6 empty] | 0%
Phase 4 - Installation | [6 empty] | 0%
Install HEDA | [6 empty] | 0%
Install HEDA package | [6 empty] | 0%
Configure HEDA settings | [6 empty] | 0%
Install Interactions for Student Recruitment | [6 empty] | 0%
Complete pre-installation steps based on documentation | [6 empty] | 0%
Install Interactions for Student Recruitment | [6 empty] | 0%
Complete post-installation steps based on documentation | [6 empty] | 0%
Phase 5 - Configuration | [6 empty] | 0%
Security Configuration | [6 empty] | 0%
Create Profiles and Permission Sets needed for granting field-level access and security/settings for objects, apps, etc. | [6 empty] | 0%
Create Roles and Groups needed for granting folder and listview access and sharing permissions for objects, reports, email templates, etc. | [6 empty] | 0%
Contact Configuration | [6 empty] | 0%
Create custom Contact fields needed on Contact and Interactions | [6 empty] | 0%
Create Interaction Mapping records based on additional fields | [6 empty] | 0%
Update Contact Page Layout | [6 empty] | 0%
Lead Configuration (If Needed) | [6 empty] | 0%
Create custom Lead fields needed on Lead and Interactions | [6 empty] | 0%
Create Interaction Mapping records based on additional fields | [6 empty] | 0%
Add standard Lead Mappings for custom Contact fields that map from Lead | [6 empty] | 0%
Update Lead Page Layout | [6 empty] | 0%
Account Configuration | [6 empty] | 0%
Create custom Account fields needed on Account | [6 empty] | 0%
Update Account Page Layouts | [6 empty] | 0%
Add standard Lead Mappings for custom Account fields if needed | [6 empty] | 0%
Opportunity Configuration | [6 empty] | 0%
Create custom Opportunity fields needed on Opportunity and Interactions | [6 empty] | 0%
Create Interaction Mapping records based on additional fields | [6 empty] | 0%
Create and configure Prospect and Applicant record types and assign Page Layouts | [6 empty] | 0%
Update Opportunity Page Layouts | [6 empty] | 0%
Configure the Opportunity Key on Interactions and in the Opportunity Key workflow based on business requirements | [6 empty] | 0%
Add standard Lead Mappings for custom Opportunity fields if needed | [6 empty] | 0%
Affiliation Configuration | [6 empty] | 0%
Create custom Affiliation fields needed on Affiliations and Interactions | [6 empty] | 0%
Create Interaction Mapping records based on additional fields | [6 empty] | 0%
Update Affiliation Page Layout | [6 empty] | 0%
Campaign Configuration | [6 empty] | 0%
Create custom Campaign fields needed on Campaigns | [6 empty] | 0%
Update Campaign Page Layout | [6 empty] | 0%
Manually create different types of Campaigns as templates (Events, Marketing, etc.) | [6 empty] | 0%
Manually add, remove, and configure Campaign Member Statuses for each type of Campaign on their templates | [6 empty] | 0%
Update the Campaign Member Status and Additional Campaign Member Status fields on Interactions with matching values for all options added to the Campaigns created | [6 empty] | 0%
Create Campaigns needed with correct Campaign Member Statuses by cloning Campaign templates in Classic | [6 empty] | 0%
Campaign Member Configuration | [6 empty] | 0%
Create custom Campaign Member fields needed on Campaign Member and Interactions | [6 empty] | 0%
Create Interaction Mapping records based on additional fields | [6 empty] | 0%
Update Campaign Member Page Layout | [6 empty] | 0%
Term Configuration | [6 empty] | 0%
Create custom Term fields needed on Terms | [6 empty] | 0%
Update Term Page Layout | [6 empty] | 0%
Plan Configuration | [6 empty] | 0%
Create custom Plan fields needed on Recruitment and Academic interests | [6 empty] | 0%
Create and configure Recruitment and Academic record types and assign Page Layouts | [6 empty] | 0%
Update Academic and Recruitment interest Layouts | [6 empty] | 0%
Phase 6: Sample Data Migration and Evaluation | [6 empty] | 0%
Load Setup Data | [6 empty] | 0%
Load Business Organization Accounts | [6 empty] | 0%
Load Educational Institution Accounts, including the University's account for Terms to look up to | [6 empty] | 0%
Load Department Accounts, including schools/colleges for interests to look up to | [6 empty] | 0%
Load Terms | [6 empty] | 0%
Load Recruitment Interests | [6 empty] | 0%
Load Academic Interests, looking up to Recruitment Interests | [6 empty] | 0%
Load Sample Data | [6 empty] | 0%
Refresh sandbox to prepare for Data Migration | [6 empty] | 0%
Data Mapping and Scrubbing (Sample group of records) | [6 empty] | 0%
Load leads (if needed) and contacts (Sample group of records) | [6 empty] | 0%
Load affiliations (Sample group of records) | [6 empty] | 0%
Evaluate Sample data | [6 empty] | 0%
Develop Reports | [6 empty] | 0%
List of Reports to be recreated in Salesforce | [6 empty] | 0%
List of new Reports to be created in Salesforce | [6 empty] | 0%
Create Report and Dashboard folders and grant access to individuals, groups, and/or roles | [6 empty] | 0%
Create Reports and Dashboards | [6 empty] | 0%
Test Configuration | [6 empty] | 0%
Test functionality and security | [6 empty] | 0%
Approve Production Environment for Power Users | [6 empty] | 0%
Phase 7: Migrate to Production | [6 empty] | 0%
Migrate configuration to Production | [6 empty] | 0%
Test configuration in Production | [6 empty] | 0%
Load Interactions to create Contacts, Affiliations, Campaign Members, and Opportunities | [6 empty] | 0%
Evaluate data | [6 empty] | 0%
Phase 8: Documentation and Training | [6 empty] | 0%
Update/Create user guides with custom configuration | [6 empty] | 0%
Train Power Users | [6 empty] | 0%
Phase 9: Go-Live for Existing Users | [6 empty] | 0%
Switch over all existing users to new platform | [6 empty] | 0%
Salesforce End User Training | [6 empty] | 0%
Communicate project completion | [6 empty] | 0%
Start Recruiting | [6 empty] | 0%